## HJ Timeline
Herff Jones Virtual Ceremony Production Timeline
| 2020-12-12 | Enter Your Ceremony Date
| On or Before | Production Milestone | Team
-40 | 2020-11-02 | Agreement Signed/Client Setup in StageClip and MarchingOrder systems | HJ
-37 | 2020-11-05 | MarchingOrder data collection website setup to your specifications | MO
-35 | 2020-11-07 | MarchingOrder/StageClip data collection websites open for student submissions | MO
-28 | 2020-11-14 | Name Recording begins | MO
-25 | 2020-11-17 | Graphics/Video due to StageClip for Individual Recognition Clips & Clip Site | SC
-16 | 2020-11-26 | MarchingOrder website closes to student submissions | MO
-14 | 2020-11-28 | Slide and audio preview ready for you to review | MO
-12 | 2020-11-30 | Platform Speeches/Ceremony Video due to StageClip | SC
-12 | 2020-11-30 | Last day to make revisions to slides or audio recordings | MO
-11 | 2020-12-01 | Deadline for Participants to submit videos to StageClip | SC
-10 | 2020-12-02 | Final day to moderate student submitted videos in StageClip client portal | SC
-9 | 2020-12-03 | MarchingOrder sends slides/audio to StageClip, final production begins | MO
-5 | 2020-12-07 | Ceremony Preview Available; Ceremony Sent for Captioning if applicable | SC
-1 | 2020-12-11 | Pre-event reminder sent to Participants with link to Clip Site | SC
-1 | 2020-12-11 | Final Approved Ceremony Video and Captioning (if applicable) loaded to school Clip Site | SC
0 | 2020-12-12 | Ceremony Date: Separate Event and Clip Notification sent to Participants | SC
4 | 2020-12-16 | Reminder to Participants who have not accessed their individual recognition clip | SC
8 | 2020-12-20 | Second Reminder to Participants who have not accessed their individual recognition clip | SC
Timelines are estimated based on a typical production workflow. Special circumstances may apply.